## CLIENT Implementation Plan
# | Type | Category | Functional Area | Description | Assigned To | Priority | Hours | Sched Date | Status | Comments | Creation Date
| Task | Project Definition | WorkPlace Central | Planning and Kick-off Meeting | All | Medium |  | KICKOFF MTG | Open | Project Planning meeting to determine objectives, scope, potential risks and define roles & responsibilities of the project team. Prepare and distribute Project Planning Guides.
| Task | Project Definition | WorkPlace Central | Complete Project Contact Information | CLIENT | Medium |  | KICKOFF MTG | Open | Base project team preferably prior to planning meeting
| Task | Project Definition | WorkPlace Central | Identify Configuration Key Users | All | Medium |  | Before KUT | Open | Identify Key Users / Decision Makers responsible for system configuration with a complete understanding of the business processes and requirements for the solution.
| Task | Project Definition | WorkPlace Central | Identify Functional Key Users | All | Medium |  | Before KUT | Open | Identify Key Users / Decision Makers that will participate in the functional training sessions.
| Task | Project Definition | WorkPlace Central | Prepare/Distribute Detailed WorkPlan - Workplace tasks | All | Medium |  | KICKOFF MTG | Open | Next steps defined and scheduled following Planning Meeting(s)
| Task | Project Definition | WorkPlace Central | Prepare/Deliver ERP EAIC Integration Design Documents | Paramount | Medium |  | Before INT mtg | Open | Prepare documentation questions for the ERP EAIC Integration Design.
| Task | Project Definition | WorkPlace Central | ERP EAIC Integration Design Review Meeting | Paramount | Medium |  | INT MTG | Open | Meeting to review the ERP Integration Design Document and Questions
| Task | Preliminary Design | WorkPlace Central | Prepare/Deliver WorkPlace Configuration Planning Guide | Paramount | Medium |  | KICKOFF MTG | Open
| Task | Preliminary Design | WorkPlace Central | WorkPlace Configuration Planning Guide Review Meeting | All | Medium |  | KICKOFF MTG | Open
| Task | Project Definition | WorkPlace Central | Determine and Schedule WorkPlace Installation and Initial, Setup/Configuration and Training Date(s) | All | Medium |  | INT MTG | Open | TBD based on ERP Test installation/minimum required configuration
| Task | Project Definition | WorkPlace Central | Prepare Microsoft SQL Server - Installed and configured | CLIENT | Medium |  | Before Install | Open | PreImplementation Requirements - Destination Hardware / Software
| Task | Project Definition | WorkPlace Central | Web server Machine/operating environment – Installed and configured, including: Internet Information Services (IIS) | CLIENT | Medium |  | Before Install | Open | PreImplementation Requirements - Destination Hardware / Software
| Task | Project Definition | WorkPlace Central | Test Financial Application and Databases – Installed and configured as intended/anticipated for Production Use. | CLIENT | Medium |  | Before Install | Open | PreImplementation Requirements - Destination Hardware / Software
| Task | Project Definition | WorkPlace Central | Provide SMTP Server for Automated email notifications | CLIENT | Medium |  | Before Install | Open | SMTP DNS Name/IP Address and setup an email Address that will be used for the “From” address on the WorkPlace eMail notifications – such as ‘WorkPlace@YOURCompany.com’
| Task | Project Definition | WorkPlace Central | Determine WorkPlace Authentication Method | CLIENT | Medium |  | Before Install | Open | PreImplementation Requirements - Destination Hardware / Software
| Task | Project Definition | WorkPlace Central | Database Backups for Test environment | CLIENT | Medium |  | Before Install | Open | Control Databases and ALL Company Databases – ensure entire test environment is included in regular nightly backup routines.
| Task | Project Definition | WorkPlace Central | Provide administrative access (or team member) to IIS and SQL Server(s) for installation and implementation activities | CLIENT | Medium |  | Before Install | Open | Require full access to both the Web Server and SQL Server machines for installation (Admin and SA [or other established System Administrative account]) in Test Environment
| Task | Project Definition | WorkPlace Central | Determine WorkPlace Installation path | CLIENT | Medium |  | INT MTG | Open | Determine the location for your ‘WorkPlace Web Server Installation Folder.’ By Default during installation the paths created will be ‘c:\program files\WorkPlace\‘ -and- ‘c:\program files\WorkPlace\SQL\’
| Task | Project Definition | WorkPlace Central | Determine WorkPlace EAIC Installation path | CLIENT | Medium |  | INT MTG | Open | Determine the location for your ‘WorkPlace EAIC Web Server Installation Folder.’ By Default during installation the paths created will be ‘c:\program files\WorkPlaceEAIC\‘ -and- ‘c:\program files\WorkPlaceEAIC\SQL\’
| Task | Project Definition | WorkPlace Central | Prepare Physical Implementation Environment(s) | CLIENT | Medium |  | Before KUT | Open | Conference/Training Room or Office with at least one Desktop or laptop computer on YOUR Network with Projector and Printer for Setup and Configuration and Maintenance Training of the WorkPlace Application.
| Task | Preliminary Design | WorkPlace Central | Completed Data Gathering with User Info for WorkPlace Setup | All | Medium |  | Before KUT | Open | Utilizing Provided Planning Guides, Determine and Gather Anticipated Setup data for WorkPlace configuration, Review of the preliminary data prior to Scheduled Configuration of the WorkPlace application.
| Task | Preliminary Design | WorkPlace Central | Preliminary Design - Configuration Items | Paramount | Medium |  | Before KUT | Open | Review Data Gathering information provided for configuration elements for preliminary design. Detailed Requirements meetings as needed.
| Task | Project Management | WorkPlace Central | Ongoing Project Management during Implementation | Paramount | Medium |  | Ongoing | Open
| Task | CRP Environment Installation | WorkPlace Central | WorkPlace SQL Objects | Paramount | Medium |  | TEST INSTALL | Open
| Task | CRP Environment Installation | WorkPlace Central | WorkPlace Web Objects | Paramount | Medium |  | TEST INSTALL | Open
| Task | CRP Environment Installation | WorkPlace Central | WorkPlace Supporting Windows Components | Paramount | Medium |  | TEST INSTALL | Open
| Task | CRP Environment Installation | WorkPlace Central | WorkPlace SQL/AD Session and Shared Users | Paramount | Medium |  | TEST INSTALL | Open
| Task | CRP Environment Installation | WorkPlace Central | Configure web.config file | Paramount | Medium |  | TEST INSTALL | Open
| Task | CRP Environment Installation | WorkPlace Central | WorkPlace IIS Application / Virtual Directory Setup | Paramount | Medium |  | TEST INSTALL | Open
| Task | CRP Environment Installation | WorkPlace Central | Load Product License certificate | Paramount | Medium |  | TEST INSTALL | Open
| Task | CRP Environment Installation | WorkPlace Central | EAIC SQL Objects | Paramount | Medium |  | TEST INSTALL | Open
| Task | CRP Environment Installation | WorkPlace Central | EAIC Web Objects | Paramount | Medium |  | TEST INSTALL | Open
| Task | CRP Environment Installation | WorkPlace Central | WorkPlace On The Go Server (OTGS) Installation | Paramount | Medium |  | TEST INSTALL | Open | Requires Time/Expense and Mobile License
| Task | CRP Environment Installation | WorkPlace Central | WorkPlace EAIC IIS Application / Virtual Directory Setup | Paramount | Medium |  | TEST INSTALL | Open
| Task | CRP Environment Installation | WorkPlace Central | Initial EAIC Settings and Data Synchronization | Paramount | Medium |  | TEST INSTALL | Open
| Task | CRP Environment Installation | WorkPlace Central | WP Agent Overview and Scheduling | Paramount | Medium |  | TEST INSTALL | Open
| Task | CRP Environment Installation | WorkPlace Central | Validate/Verify System Installation | Paramount | Medium |  | TEST INSTALL | Open
| Task | CRP Environment Installation | WorkPlace Central | Validate/Verify System Installation by Consultant | Paramount | Medium |  | TEST INSTALL | Open | Connect to System and Verify system against SOW.
| Task | CRP Configuration Key User Training | WorkPlace Central | Accessing WorkPlace | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Accessing On-line Help Documentation | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | WorkPlace About | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | WorkPlace Navigation | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | User Preferences | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Announcements | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Country Maintenance | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Global Settings | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | System Settings | All | Medium |  | ADMIN KUT SESSION 1 | Open | Define parameters, global to all users setup in WorkPlace.
| Task | CRP Configuration Key User Training | WorkPlace Central | Departments | All | Medium |  | ADMIN KUT SESSION 1 | Open | All employees within the WorkPlace application must belong to at lease one department. Additionally, automatic restrictions for General Ledger account number selection, based on the Department selected during requisition entry can be created.
| Task | CRP Configuration Key User Training | WorkPlace Central | Companies | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Inter-Company / Inter-Company Relationship | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Company Address | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Security | All | Medium |  | ADMIN KUT SESSION 1 | Open | All users who will perform any action - enter or approve a time, expense, establish projects, etc. - within the WorkPlace application must be setup in WorkPlace Security and granted the appropriate 'access' to functions within the application modules. Security is where this is performed as well as establishing and/or linking the home department, email notifications and users restrictions to the users login.
| Task | CRP Configuration Key User Training | WorkPlace Central | Role Based Security | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Approval Lists | All | Medium |  | ADMIN KUT SESSION 2 | Open | WorkPlace requires that approvers be established for use with Routing Rules. Approval list setup defines which users are Approvers as well as establishing their pre-defined Alternates. Before approval lists can be setup, users with access to the approval session must be established in WorkPlace Security.
| Task | CRP Configuration Key User Training | WorkPlace Central | Non-Financial Lists | All | Medium |  | ADMIN KUT SESSION 2 | Open | Non-Financial Lists give you the ability to create lists of values for data entry/selection fields within the Workplace application. Once created, these lists can then be used with User Defined Field Templates to create restrictions and/or requirements for data selection in these fields.
| Task | CRP Configuration Key User Training | WorkPlace Central | Routing Rules | All | Medium |  | ADMIN KUT SESSION 2 | Open | Define how a record is processed and who it must be routed to during the approval process. Records that meet the established criteria (filters on the routing rule) will be routed to an approval session. Routing Rules define the hierarchy of tolerance rules, and the impact they have on the approval process. These rules are established by group (or role) when using the role-based security option, within the routing rule filters are defined to determine where each document/line item, based on the returned criteria, will be routed.
| Task | CRP Configuration Key User Training | WorkPlace Central | Note Codes | All | Medium |  | ADMIN KUT SESSION 1 | Open | Used during Approval and Review sessions when time and/or and expense item will NOT be approved (these are notes back to the document creator).
| Task | CRP Configuration Key User Training | WorkPlace Central | User Defined Field Templates | All | Medium |  | ADMIN KUT SESSION 1 | Open | This specifies by WorkPlace user, fields with default input, required fields, hidden fields and/or read only fields. Once the template has been created it must then be 'assigned' to a the user in WorkPlace Security to take effect.
| Task | CRP Configuration Key User Training | WorkPlace Central | Filter Templates | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | User Defined Lists | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Catalog Maintenance | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Organization | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Payment Terms | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Shipping Method | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Tax | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Tax Schedule | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Metrics | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Distribution Group Maintenance | All | Medium |  | ADMIN KUT SESSION 1 | Open | Distribution Group Maintenance and Import requires a GL Distributions license
| Task | CRP Configuration Key User Training | WorkPlace Central | Documents | All | Medium |  | ADMIN KUT SESSION 1 | Open | Requires WorkPlace Document Management license
| Task | CRP Configuration Key User Training | WorkPlace Central | Currency | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Exchange Rate | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Exchange Rate Type | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | G/L Account | All | Medium |  | GL KUT SESSION | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | G/L Account Group | All | Medium |  | GL KUT SESSION | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | G/L Analysis | All | Medium |  | GL KUT SESSION | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | G/L Analysis Group | All | Medium |  | GL KUT SESSION | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | G/L Analysis Group Account | All | Medium |  | GL KUT SESSION | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | G/L Budget | All | Medium |  | GL KUT SESSION | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | G/L Period | All | Medium |  | GL KUT SESSION | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | G/L Posting Codes and Posting Hierarchy | All | Medium |  | GL KUT SESSION | Open | Required for Inventory and Purchasing Accruals
| Task | CRP Configuration Key User Training | WorkPlace Central | G/L Segment | All | Medium |  | GL KUT SESSION | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Vendor / Vendor Addresses | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Vendor Class | All | Medium |  | ADMIN KUT SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Budgets | All | Medium |  | BUDGET KUT SESSION | Open
| Task | CRP Configuration Key User Training | Requisition | Solution Specific System Settings | All | Medium |  | RQ KUT SESSION | Open
| Task | CRP Configuration Key User Training | Requisition | Attachment Requirements | All | Medium |  | RQ KUT SESSION | Open | Available with RFQ license
| Task | CRP Configuration Key User Training | Requisition | Expense Types | All | Medium |  | RQ KUT SESSION | Open
| Task | CRP Configuration Key User Training | Requisition | Shopping Lists | All | Medium |  | RQ KUT SESSION | Open
| Task | CRP Configuration Key User Training | Requisition | Priority Maintenance | All | Medium |  | RQ KUT SESSION | Open
| Task | CRP Configuration Key User Training | Requisition | Vendor Information | All | Medium |  | RQ KUT SESSION | Open
| Task | CRP Configuration Key User Training | Purchasing | Solution Specific System Settings | All | Medium |  | PO KUT SESSION | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Vendor Contracts | All | Medium |  | VC KUT SESSION | Open
| Task | CRP Configuration Key User Training | WorkPlace Project | Solution Specific System Settings | All | Medium |  | PROJECT KUT SESSION | Open
| Task | CRP Configuration Key User Training | WorkPlace Project | Activity Maintenance | All | Medium |  | PROJECT KUT SESSION | Open
| Task | CRP Configuration Key User Training | WorkPlace Project | Budget Type | All | Medium |  | PROJECT KUT SESSION | Open
| Task | CRP Configuration Key User Training | WorkPlace Project | Labor Group Maintenance | All | Medium |  | PROJECT KUT SESSION | Open
| Task | CRP Configuration Key User Training | WorkPlace Project | Project Status Maintenance | All | Medium |  | PROJECT KUT SESSION | Open
| Task | CRP Configuration Key User Training | WorkPlace Project | Project Type Maintenance | All | Medium |  | PROJECT KUT SESSION | Open
| Task | CRP Configuration Key User Training | WorkPlace Project | Shift Maintenance | All | Medium |  | PROJECT KUT SESSION | Open
| Task | CRP Configuration Key User Training | WorkPlace Project | Project Setup and Maintenance | All | Medium |  | PROJECT KUT SESSION | Open
| Task | CRP Configuration Key User Training | Time | Solution Specific System Settings | All | Medium |  | TIME KUT | Open
| Task | CRP Configuration Key User Training | Time | Time Periods | All | Medium |  | TIME KUT | Open
| Task | CRP Configuration Key User Training | Time | Time Types | All | Medium |  | TIME KUT | Open
| Task | CRP Configuration Key User Training | Time | Earning Codes | All | Medium |  | TIME KUT | Open
| Task | CRP Configuration Key User Training | Expense | Solution Specific System Settings | All | Medium |  | EXPENSE KUT SESSION | Open
| Task | CRP Configuration Key User Training | Expense | Time Periods | All | Medium |  | EXPENSE KUT SESSION | Open
| Task | CRP Configuration Key User Training | Expense | Credit Card Types | All | Medium |  | EXPENSE KUT SESSION | Open
| Task | CRP Configuration Key User Training | Expense | Expense Types | All | Medium |  | EXPENSE KUT SESSION | Open
| Task | CRP Configuration Key User Training | Expense | Questionnaires | All | Medium |  | EXPENSE KUT SESSION | Open
| Task | CRP Configuration Key User Training | Expense | Payment Methods | All | Medium |  | EXPENSE KUT SESSION | Open
| Task | CRP Configuration Key User Training | Inventory | Solution Specific System Settings | All | Medium |  | INV SESSION 1 | Open
| Task | CRP Configuration Key User Training | Inventory | Commodity | All | Medium |  | INV SESSION 1 | Open
| Task | CRP Configuration Key User Training | Inventory | Locations | All | Medium |  | INV SESSION 1 | Open
| Task | CRP Configuration Key User Training | Inventory | Item Groups | All | Medium |  | INV SESSION 1 | Open
| Task | CRP Configuration Key User Training | Inventory | Inventory Adjustment Reason Codes | All | Medium |  | INV SESSION 1 | Open
| Task | CRP Configuration Key User Training | Inventory | Units of Measure | All | Medium |  | INV SESSION 1 | Open
| Task | CRP Configuration Key User Training | Inventory | Unit of Measure Conversion Groups | All | Medium |  | INV SESSION 1 | Open
| Task | CRP Configuration Key User Training | Inventory | Items | All | Medium |  | INV SESSION 1 | Open
| Task | CRP Configuration Key User Training | WorkPlace Central | Complete Sample Configurations in preparation for Functional Training | All | Medium |  | Before Functional Training | Open
| Task | CRP Functional Key User Training | Requisition | Requisition Entry | All | Medium |  | RQ KUT SESSION | Open
| Task | CRP Functional Key User Training | Requisition | Check Request Entry | All | Medium |  | RQ KUT SESSION | Open
| Task | CRP Functional Key User Training | Requisition | Inventory Release / Transfer Requisition Entry | All | Medium |  | RQ KUT SESSION | Open
| Task | CRP Functional Key User Training | Requisition | Requisition Delegation | All | Medium |  | RQ KUT SESSION | Open
| Task | CRP Functional Key User Training | Requisition | Requisition Approval | All | Medium |  | RQ KUT SESSION | Open
| Task | CRP Functional Key User Training | Requisition | Requisition Review | All | Medium |  | RQ KUT SESSION | Open
| Task | CRP Functional Key User Training | Requisition | Requisition RFQ Maintenance and Processing | All | Medium |  | RQ KUT SESSION | Open
| Task | CRP Functional Key User Training | Requisition | Functional Process Solution Testing | All | Medium |  | RQ KUT SESSION | Open
| Task | CRP Functional Key User Training | Time | Timesheet Entry | All | Medium |  | TIME KUT | Open
| Task | CRP Functional Key User Training | Time | Timesheet Approval | All | Medium |  | TIME KUT | Open
| Task | CRP Functional Key User Training | Time | Timesheet Approval Override | All | Medium |  | TIME KUT | Open
| Task | CRP Functional Key User Training | Time | Timesheet Batch Process | All | Medium |  | TIME KUT | Open
| Task | CRP Functional Key User Training | Time | Functional Process Solution Testing | All | Medium |  | TIME KUT | Open
| Task | CRP Functional Key User Training | Expense | Expense Sheet Entry | All | Medium |  | EXPENSE KUT SESSION | Open
| Task | CRP Functional Key User Training | Expense | Credit Card Import | All | Medium |  | EXPENSE KUT SESSION | Open
| Task | CRP Functional Key User Training | Expense | Expense Sheet Approvals | All | Medium |  | EXPENSE KUT SESSION | Open
| Task | CRP Functional Key User Training | Expense | Expense Sheet Batch Process | All | Medium |  | EXPENSE KUT SESSION | Open
| Task | CRP Functional Key User Training | Expense | Functional Process Solution Testing | All | Medium |  | EXPENSE KUT SESSION | Open
| Task | CRP Functional Key User Training | Purchasing | Purchase Order Entry | All | Medium |  | PO KUT SESSION | Open
| Task | CRP Functional Key User Training | Purchasing | Purchase Order / Change Order Management | All | Medium |  | PO KUT SESSION | Open
| Task | CRP Functional Key User Training | Purchasing | Purchase Order Approvals | All | Medium |  | PO KUT SESSION | Open
| Task | CRP Functional Key User Training | Purchasing | Auto-Receiving Entry | All | Medium |  | RCV/INV KUT SESSION | Open
| Task | CRP Functional Key User Training | Purchasing | Receive / Match Invoice Entry | All | Medium |  | RCV/INV KUT SESSION | Open
| Task | CRP Functional Key User Training | Purchasing | Receive / Match Invoice Approvals | All | Medium |  | RCV/INV KUT SESSION | Open
| Task | CRP Functional Key User Training | Purchasing | G/L Journal Batch Post | All | Medium |  | RCV/INV KUT SESSION | Open
| Task | CRP Functional Key User Training | Purchasing | Functional Process Solution Testing | All | Medium |  | RCV/INV KUT SESSION | Open
| Task | CRP Functional Key User Training | Inventory | Inventory Release Request Entry | All | Medium |  | INV SESSION 2 | Open
| Task | CRP Functional Key User Training | Inventory | Inventory Transfer Request Entry | All | Medium |  | INV SESSION 2 | Open
| Task | CRP Functional Key User Training | Inventory | Inventory Release/Transfer Ship Entry | All | Medium |  | INV SESSION 2 | Open
| Task | CRP Functional Key User Training | Inventory | Inventory Release/Transfer Receipt Entry | All | Medium |  | INV SESSION 2 | Open
| Task | CRP Functional Key User Training | Inventory | Inventory Cost Layer Adjustment Entry | All | Medium |  | INV SESSION 2 | Open
| Task | CRP Functional Key User Training | Inventory | Inventory Adjustment Entry | All | Medium |  | INV SESSION 2 | Open
| Task | CRP Functional Key User Training | Inventory | Inventory Physical Count Entry | All | Medium |  | INV SESSION 2 | Open
| Task | CRP Functional Key User Training | Inventory | Inventory Replenishment | All | Medium |  | INV SESSION 2 | Open
| Task | CRP Functional Key User Training | Inventory | G/L Journal Batch Post | All | Medium |  | INV SESSION 2 | Open
| Task | CRP Functional Key User Training | Inventory | Functional Process Solution Testing | All | Medium |  | INV SESSION 2 | Open
| Task | CRP Functional Key User Training | Inventory Handhelds | Adjustment Entry | All | Medium |  | INV SESSION 3 | Open
| Task | CRP Functional Key User Training | Inventory Handhelds | Case Usage Entry | All | Medium |  | INV SESSION 3 | Open
| Task | CRP Functional Key User Training | Inventory Handhelds | Remove from Case Entry | All | Medium |  | INV SESSION 3 | Open
| Task | CRP Functional Key User Training | Inventory Handhelds | Receive PO | All | Medium |  | INV SESSION 3 | Open
| Task | CRP Functional Key User Training | Inventory Handhelds | Transfer Ship | All | Medium |  | INV SESSION 3 | Open
| Task | CRP Functional Key User Training | Inventory Handhelds | Transfer Receipt | All | Medium |  | INV SESSION 3 | Open
| Task | CRP Functional Key User Training | Inventory Handhelds | Item Maintenance / Inquiry | All | Medium |  | INV SESSION 3 | Open
| Task | CRP Functional Key User Training | Inventory Handhelds | Functional Process Solution Testing | All | Medium |  | INV SESSION 3 | Open
| Task | User Acceptance Testing | WorkPlace Central | Review Requirements for balance of System Setup | All | Medium |  | Before UAT | Open
| Task | User Acceptance Testing | WorkPlace Central | System Setup Completed | CLIENT | Medium |  | Before UAT | Open
| Task | User Acceptance Testing | WorkPlace Central | Create UAT Test Plan | CLIENT | Medium |  | Before UAT | Open
| Task | User Acceptance Testing | WorkPlace Central | Conference Room Pilot | CLIENT | Medium |  | UAT Session | Open | Paramount time will be scheduled to support CRP activities.
| Task | User Acceptance Testing | WorkPlace Central | Complete WorkPlace Solution Test | CLIENT | Medium |  | UAT Session | Open
| Task | User Acceptance Testing | WorkPlace Central | Detailed Design Review and Updates | All | Medium |  | UAT Session | Open
| Task | User Acceptance Testing | WorkPlace Central | UAT Sign Off and Confirmation of Go Live | All | Medium |  | UAT Session | Open
| Task | End User Training | WorkPlace Central | Identify Trainers and Attendees | CLIENT | Medium |  | Before EUT | Open
| Task | End User Training | WorkPlace Central | End User Documentation | CLIENT | Medium |  | Before EUT | Open | Produce Client specific user and system administration procedures. Assemble end-user training materials using procedures as a basis. WorkPlace Standard and/or Other documentation as noted in the engagement is provided.
| Task | End User Training | WorkPlace Central | End User Training | CLIENT | Medium |  | EUT SESSION 1 | Open | Utilizing the Test Environment, perform End-user training prior to Go live on the new system.
| Task | Prepare Production Environment | WorkPlace Central | End User Support | CLIENT | Medium |  |  | Open | The Project Team is available to support the user during Go Live. Document, prioritize and resolve issues.
| Task | Prepare Production Environment | WorkPlace Central | Production Installation | All | Medium |  | LIVE INSTALL | Open
| Task | Prepare Production Environment | WorkPlace Central | Migration of Test Environment Configuration | All | Medium |  | LIVE INSTALL | Open
| Task | Go Live | WorkPlace Central | Post Implementation Support/Assistance | Paramount | Medium |  | POST GOLIVE | Open
| Task | Go Live | WorkPlace Central | Support Hand Off | Paramount | Medium |  | POST GOLIVE | Open | Hand Off Meeting with Paramount Support team and Client Account Manager (CAM)

## Follow Up Actions
Action | Assigned To | Due Date | Completion Date | Status | Comment

## Lookups
Type | Categories | Functional Area | Status | Assigned To | Priority
Task | Project Definition | WorkPlace Central | Open | CLIENT | High
Issue | Preliminary Design | Requisition | Closed | Paramount | Medium
Gap | Project Management | Purchasing | On Hold | All | Low
| CRP Environment Installation | Invoice Automation | In Process |  | NTH
| CRP Configuration Key User Training | Inventory
| CRP Functional Key User Training | Time
| User Acceptance Testing | Expense
| End User Training | WorkPlace Project
| Prepare Production Environment | Inventory Handhelds
Go Live
Note on C1: Update as required based on SOW deliverables, phase, functional area